# Appendix 2: Collective actions

The implementation report for collective actions was submitted by the 31 December 2020 and quality assured through a final review at BDC(1)2020.

| Symbols used for implementation reporting of collective actions Any action row can have up to 3 symbols |  |
| --- | --- |
| Symbol | Meaning |
|  | Not implemented |
|  | In progress / partially complete |
|  | Ongoing task |
|  | Part of the assessment-cycle |
|  | Implemented / Completed no further work required |

| No | Action | Habitats/ Species | Region | Lead Party (ies) | Lead party in place? | Action sheet developed? | Action implemented? | Implementation reporting comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Building on existing material (e.g. OSPAR website) develop and implement a phased communications strategy for OSPAR listed species and habitat | All | All | Secretariat |  |  |  | An information leaflet on the roadmap has been prepared www.ospar.org/site/assets/files/35421/posh_roadmap_info_doc.pdf Links to case reports and implementation highlights have been added to the species and habitats dropdown ospar.org/work-areas/bdc/species-habitats/list-of-threatened-declining-species-habitats A page on the implementation of species and habitats Recommendations has been created ospar.org/work-areas/bdc/species-habitats/implementation-of-species-and-habitat-recommendations A template for feature specific pages has been developed. The Secretariat will develop the feature specific pages and populate them with information as work progresses, and e.g. the feature specific status assessments are completed. |
| 2 | Improve the OSPAR habitat mapping database in relation to all Habitats, and publish regularly updated quality assessments and distribution records | All habitats | All | United Kingdom |  |  |  | A process has been set up ensuring that every 1-2 years (depending on requirements) a data call is sent out and point and polygon datasets of threatened and/or declining species and habitats are submitted for ingestion into the database. A draft version of the database is share with POSH and a final version with BDC. Data are publicly available through the EMODnet map viewer (https://www.emodnet-seabedhabitats.eu/access-data/launch-map-viewer/) |
| 3 | Develop and implement an appropriate monitoring and assessment strategy addressing the distribution, extent and condition of coastal habitats, coordinating activities to build on existing monitoring work and where possible developing synergy with monitoring of other species and habitats. | Sabellaria spinulosa reefs; littoral chalk communities; Ostrea edulis beds; Zostera beds; Modiolus modiolus beds; Cymodocea meadows; and, Maerl beds | All | United Kingdom |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. Consideration needs to be given to whether this can be delivered as a collective action as currently worded or interpret as national monitoring, with sharing of good practice and delivery through status assessments. Experts at ICG-POSH and ICG-COBAM were engaged in efforts to identify the final output which would be required from this action, but there was a lack of understanding about the purpose of the action making it difficult to proceed with the next step. |
| 4 | Request and review ICES advice, and other fisheries assessments based on monitoring and fisheries survey information | Sturgeon, Allis shad, European eel, cod, orange roughy, sea lamprey), common skate species complex, white skate, Angel shark, basking shark, spurdog, gulper shark, leafscale gulper shark, Portugese dogfish, porbeagle, spotted ray, thornback ray, quahog, Azorean limpet, harbour porpoise | All | (Secretariat and/or ICG-POSH conveners) |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. ICES advice in progress for Gulper shark, Leafscale gulper shark, Portuguese dogfish OSPAR 2019 to consider ICES advice request for 1) Angel shark, Common skate complex (Flapper skate and Blue skate), Spotted ray, Thornback ray/skate and White skate 2) Basking shark, Porbeagle and Spurdog. |
| 5 | Develop and implement a monitoring strategy, as part of the JAMP, leading to the periodic assessment of the status of species, to promote and coordinate the collection of information on distribution, status of, threats to and impacts on the species, using as appropriate information from other competent authorities | Loggerhead turtle, Leatherback turtle, Bowhead whale, Blue whale, Northern right whale, Lesser black-backed gull, Ivory gull, Little shearwater, Balearic shearwater, Black-legged kittiwake, Roseate tern,Thick-billed murre, Steller’s eider, Iberian guillemot, Ostrea edulis, long snouted Seahorse, short snouted seahorse | All |  |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. JWG BIRD will address bird species. For other species Lead Contracting Party(ies), supported by France and United Kingdom. ICG-COBAM, ICG-POSH |
| 6 | In the context of Article 4 Annex V of the Convention and in line with the common understanding (OSPAR 13/13), cooperate with relevant competent organisations to develop a strategy to encourage commercial fishermen to report incidental by-catches key habitat forming species, including information about location and date. | Lophelia pertusa reefs, coral gardens, Deep-sea sponge aggregations, seapen and burrowing megafauna, | All | Secretariat |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. The neighbouring Regional Seas Conventions OSPAR and HELCOM organised a joint workshop on 3-5 September 2019 to progress work on assessing the pressure from incidental by-catch of birds and marine mammals. The workshop was a forum to progress work on assessing the pressure from incidental by-catch and developing regional indicators. The workshop focussed on seabirds and marine mammals with the intention of developing concepts which could be applied to other species groups in the future (i.e. species of relevance to this action) |
| 7 | Carrying out appropriate periodic monitoring, where appropriate this could include visual observation e.g. video of habitat presence and condition at selected sites, and evidence of pressures such as trawling damage, ghost fishing and percentage cover of live and dead or destroyed coral | Carbonate mounds, Sabelleria spinulosa reefs | III, V | United Kingdom |  |  |  | No work has yet been taken as this action was due to be included in the next phase of the JAMP post 2021. Options for implementing this action through an alternative approach were considered at ICG-POSH 2019. |
| 8 | Compile evidence on the species and habitats that form on carbonate mounds, hydrothermal vents and seamounts in the OSPAR Maritime Area and assess which are threatened by on going and potential human activities | Carbonate mounds; hydrothermal vents; seamounts | V | No Lead Supported by France, Norway and the United Kingdom , ICG-COBAM |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 9 | Evaluate the extent to which ecological data from commercial Nephrops stock assessment and commercial video footage and photographic evidence can be used to assess the status of sea‐pen and burrowing megafauna communities, and as appropriate develop protocols for assessment purposes. | Seapen and burrowing megafauna | II, III | United Kingdom |  |  |  | An Action Development Sheet was submitted by the UK to ICG-POSH 2017 and updated in 2018. Informal discussions have continued, and other Contracting Parties are currently identifying lead contacts for a project steering group. |
| 10 | Monitor key pressures including loss and change of substratum, levels of eutrophication, removal of species, introduction and spread of non‐indigenous species and physical damage | Littoral chalk | II |  |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 11 | Gather contextual information on activities, such as aggregate dredging, offshore development or fishing, likely to have an effect on Sabellaria spinulosa reefs in the vicinity of areas selected for monitoring | Sabelleria spinulosa reefs | II, III | Netherlands, UK and Norway |  |  |  | Development of action sheet is not yet initiated due to other priorities. |
| 12 | Analyse whether any of the key areas justify selection as MPAs for the protection of whales populations and whether such areas may become a component of the OSPAR MPA network | Bowhead whale, Blue whale, Northern right whale, Harbour porpoise | All | Germany |  |  |  | Steps taken include a completed literature and data review, and preparatory work on the model approach. Sophisticated modelling is to be conducted to identify key areas. Development of a sound scientific modelling approach will require input from modelling experts. Expert consultations are envisaged in 2020. Data deficiencies for some species may severely limit (or even make impossible) the development of sound scientific models. And as a consequence, tasks may need more time than originally envisaged. Data paucity for the Northern right whale, a species extirpated in the OSPAR Maritime Area, makes identification of key areas impossible. Thus, processing for the Norther right whale has stopped and Action 12 is considered ‘completed’ for this species. |
| 13 | Evaluate the extent to which critical habitat for the following species are already included within the OSPAR network of marine protected areas, and whether this coverage can be improved as a complementary measure to other conservation and management measures | Spurdog, Gulper shark, Leafscale Gulper shark, Portuguese dogfish, Porbeagle shark, Spotted ray, Thornback ray, Harbour porpoise, Atlantic salmon | All | Germany |  |  |  | Steps already taken, e.g. - literature and data review completed, - preparatory work on model approach conducted. Sophisticated modelling has to be conducted to identify critical habitat. Development of a sound scientific modelling approach will require input from modelling experts. Thus, expert consultations are envisaged in 2020. Data deficiencies for some Action 13 species, especially for some deep-sea shark species, may severely limit (or even make impossible) the development of sound scientific models. And as a consequence, tasks may need more time than originally envisaged. |
| 14 | Promote their inclusion as a protected species in other relevant biodiversity conventions | Sea lamprey, Allis shad, European eel, Sturgeon, Orange roughy, Atlantic salmon, Common skate, White skate, Angel shark, Basking shark | All | Lead Contracting Party(ies), Supported by France and the Netherlands ICG-POSH, BDC |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. |
| 15 | In the context of Article 4 of Annex V of the Convention and in line with the common understanding (OSPAR 13/13), draw to the attention of relevant competent organisations instances where fishing activities constitute a threat to relevant species and habitats and where appropriate encourage those organisations to take appropriate measures | Lophelia pertusa reefs, Coral gardens, Deep-sea sponge aggregations, Carbonate mounds, Hydrothermal vents, Sea pen and burrowing megafauna, Seamounts; Maerl beds, Ostrea edulis beds Cymodocea, Sabellaria spinulosa reefs, Modiolus modiolus beds sturgeon, Allis shad, European eel, Cod, Orange roughy, Sea lamprey, Atlantic Salmon, Common skate, White skate, Angel shark, Basking shark, Spurdog, Gulper shark, Leafscale gulper shark, Portugese dogfish, Porbeagle, Spotted ray, Thornback ray, Iberian guillemot, Ostrea edulis and Ostrea edulis beds | All | Lead Contracting Parties for status assessments, Supported by France and the Secretariat ICG-POSH, BDC |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 16 | In the context of Article 4 of Annex V of the Convention and in line with the common understanding (OSPAR 13/13), draw to the attention of relevant competent organisations instances where other physical disturbance to seafloor (e.g. mineral extraction, biological and geological sampling, construction) constitute a threat to relevant habitats and where appropriate encourage those organisations to take appropriate measures | Hydrothermal vents; Seamounts; Ostrea edulis beds, Cymodocea, Sabellaria spinulosa reefs. | All | Lead Contracting Parties, supported by France, Norway and the Secretariat ICG-POSH, EIHA |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 17 | In the context of Article 4 of Annex V of the Convention and in line with the common understanding (OSPAR 13/13), draw to the attention of relevant competent organisations instances where ship noise and ship strikes constitute a threat to relevant species and where appropriate encourage those organisations to take appropriate measures | Northern right Whale, Blue whale, Bowhead whale, Harbour porpoise, Loggerhead turtle, Leatherback turtle | All | Lead Contracting Party(ies), supported by France ICG-Noise ICG-POSH, EIHA |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 18 | In the context of Article 4 of Annex V of the Convention and in line with the common understanding (OSPAR 13/13), draw to the attention of relevant competent organisations instances where entanglement and ingestion of marine Litter and ADLFG constitute a threat to relevant species and where appropriate encourage those organisations to take appropriate measures | Leatherback turtle, Loggerhead turtle, Leafscale Gulper shark, Portugese Dogfish, Blue whale, Bowhead whale, Northern right whale | All | ICG-ML (Secretariat support) |  |  |  | In part this action will be implemented through a regular cycle of assessments. However, in addition OSPAR Common Indicators are in place for ingestion of marine litter by Fulmars and turtles, which provide evidence of changes in pressure. Future work in ICG-ML will provide further regional-scale evidence on harm, to be included in the thematic assessment for the OSPAR Quality Status Report 2023. |
| 19 | In the context of Article 4 of Annex V of the Convention and in line with the common understanding (OSPAR 13/13), draw to the attention of relevant competent organisations instances where pollution from oil and hazardous substances constitute a threat to relevant species and where appropriate encourage those organisations to take appropriate measures | Loggerhead turtle, Leatherback turtle, European eel, Iberian guillemot | All | Co-Conveners to raise with HASEC and OIC supported by France and [Spain] HASEC |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 20 | Cooperate and coordinate with other relevant competent international organisations and bodies, drawing upon the actions and measures suggested in the Background Document (OSPAR publication 2010/480) to address threats from aquaculture activities | Cymodocea, Maerl beds, Atlantic salmon | All | Co-Conveners to raise with EIHA supported by Norway EIHA |  |  |  | Implementation of this action needs to be reconsidered, re-grouping the features may help bring more accuracy to the description of the concrete action which needs to be implemented. Only the Background Document for salmon refers to this specific action. |
| 21 | Cooperate and coordinate with other relevant competent international organisations and bodies, drawing upon the actions and measures suggested in the Background Document (OSPAR publication 2010/480) to address threats from habitat alteration or loss, obstacles to migration and pollution | European eel, Atlantic salmon | I, II, III, IV | Secretariat |  |  |  | Implementation of this action needs to be reconsidered, re-grouping the features may help bring more accuracy to the description of the concrete action which needs to be implemented. Only the Background Document for salmon refers to this specific action. |
| 22 | Identify whether further measures to maintain or improve water quality (contaminants and nutrients) are necessary to safeguard relevant habitats and implement if required | Maerl beds, Zostera beds, Mytulis edulis beds, Cymodocea; Intertidal mudflats | I, II, III, IV | Lead Contracting party for Status assessment HASEC |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. Status assessment of Maerl beds was carried out in the meeting cycle 2019/2020 as a first step for this action. |
| 23 | Consider whether existing and new measures to manage the impacts of pressures both within and outside waters under their national jurisdiction require additional action through the OSPAR Commission; | Littoral chalk, Ostrea edulis beds | II, III, IV | Lead Contracting Party(ies), supported by Belgium ICG-POSH |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. |
| 24 | Developing, within the competence of OSPAR, effective mitigation actions against further anthropogenic threats to whale populations and incorporate them into appropriate measures for the protection of these species; | Blue whale, Bowhead whale, Northern right whale | All | Lead Contracting Party(ies), supported by France EIHA, ICG-Noise, ICG-ML |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. Status assessments of Blue whale, Bowhead whale, Northern right whale were carried out in the meeting cycle 2019/2020 as a first step for this action. |
| 25 | Develop and incorporate appropriate measures to mitigate habitat destruction (e.g. caused by degradation of spawning habitats through silting due to agriculture intensification or dams; maintenance dredging and sand and gravel extraction) and degradation of the water quality in estuaries; | Sea Lamprey, Sturgeon | I, II, III and IV | EIHA |  |  |  | Implementation of this action needs to be reconsidered, the action seems to group several different pressures and activities which may need to be re-grouped . |
| 26 | Develop and/or refine relevant measures and strategies for preventing and reducing impact on turtles of entanglement in and ingestion of marine litter (in particular plastic bags), pollution, collision and bycatch | Leatherback turtle, Loggerhead turtle | All | France |  |  |  | A Scoping Document has been prepared, based on elements provided by participating CPs, on the measures aiming to prevent or reduce impacts of human activities on turtles, with the objective to share national or/and local initiatives to provide an overview and help formulating recommendations on further actions. |
| 27 | Advocate management measures (for example, management measures in marine protected areas such as Natura 2000 sites, OSPAR MPAs or address necessary measures under the Marine Strategy Framework Directive (MSFD) with the appropriate authorities. | Ocean quahog | II | Co-Conveners to raise with ICG-MPA supported by the Netherlands and United kingdom EIHA, ICG-MPA |  |  |  | Implementation of this action needs to be reconsidered, the action appears to focus on issues under national competency and whether any aspects could be taken forward as collective efforts appears unclear. |
| 28 | Where applicable, ensure the implementation of the Marine Strategy Framework Directive, by working to achieve good environmental status of habitats essential to the life cycles of cod and the cod stocks, including age and size structure of cod populations, as well as their role in the marine food web. | Cod | II and III |  |  |  |  | Implementation of this action needs to be reconsidered, the action appears to focus on issues under EU competency to assess which could be proposed for further consideration to ICG-MSFD. BDC 2018 discussed whether Action 28 could be considered completed. The EU highlighted that Article 8 of the Common Fisheries Policy provide member states a mechanism to identify and take management action on Critical Habitats. The Netherlands highlighted the link to the MPA eco-coherence connectivity and lifecycle analysis that they were undertaking, highlighting that cod was one of the species where they had the best data. BDC agreed that Action 28 should remain in the roadmap and a link should be made to the work on eco-coherence in ICG-MPA. |
| 29 | Develop guidelines on how to minimise the disturbing and/or harmful acoustic effects to harbour porpoises especially from seismic surveys, pile driving, shipping traffic, military activities and underwater explosions; | Harbour porpoise | II and III | Netherlands |  |  |  | This action is forwarded to ICG Noise. It was placed on the agenda of the autumn 2019 meeting. ICG-Noise is preparing an assessment of the risk of impacts from impulsive noise on harbour porpoise; an inventory of noise mitigation measures is partially complete – it will cover all major activities and is relevant to all sensitive receptors including harbour porpoise |
| 30 | Take measures to further reduce discharges, emissions and losses of relevant hazardous substances to a level, that is compatible with breeding success of European eel, referred to in the background document; | European eel | I, II, III and IV | Lead Contracting Party(ies), supported by France HASEC |  |  |  | Implementation of this action needs to be reconsidered, relevant action is taken by other actors and competent authorities and the added value of OSPAR collective action needs to be identified before further steps can be taken. |
| 31 | Develop measures within OSPAR’s competence to reduce or eliminate the impact of habitat alteration from human activities on the Ostrea edulis and Ostrea edulis beds through bottom disturbance | Ostrea edulis and Ostrea edulis beds | II | Lead Contracting Party(ies), supported by Belgium EIHA, NORA network |  |  |  |  |
| 32 | Develop relevant measures for preventing and reducing oil pollution within OSPAR Region IV; | Iberian guillemot | IV | Spain |  |  |  | Steps to implement the action have not yet been taken. Preparatory work has been initiated and further action is foreseen starting in 2020. |
| 33 | Improve coordination of research to improve understanding of life history, distribution, track trends in populations and address specific issues identified in the Recommendations | Sturgeon, Allis shad, European eel, Cod, Orange roughy, Sea lamprey, Atlantic salmon, Common skate, White skate, Angel shark, Basking shark, Spurdog, gulper shark, Leafscale Gulper shark, Portugese dogfish, Porbeagle, Spotted ray, Thornback ray | All | Lead Contracting Party(ies), supported by Norway ICG-POSH, ICG-COBAM, Science Needs Agenda |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. OSPAR issued an advice request to ICES in 2018 to assess gulper shark, leafscale gulper shark and Portuguese dogfish. Two additional advice requests were issued to ICES in 2019 to assess common skate, white skate, angel shark, basking shark, porbeagle, spotted ray and thornback ray. The status assessments would form the basis for any further action. |
| 34 | Coordinate with fisheries research and funding agencies to consider the establishment of a collaborative fisheries-independent research programme to evaluate the status of the species, monitor stock recovery and track movements, and identify any networks of critical habitats; | Common skate, White skate, Angel shark, Basking shark, Spurdog, Gulper shark, Leafscale gulper shark, Portugese Dogfish, Porbeagle, Spotted ray, Thornback ray | All | No lead ICG-POSH, ICG-COBAM, ICG-MPA, BDC |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. |
| 35 | Maintain cooperation with ICES and fisheries organisations to get regular advice and to coordinate monitoring and research programs. Link with IUCN and wider academic research networks for non-commercial species. | Sturgeon, Allis shad, European eel, Cod, Orange roughy, Sea lamprey, Atlantic salmon, Leatherback turtle, Loggerhead turtles | All | No Lead, Supported by France and Norway ICG-POSH, ICG-COBAM |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. |
| 36 | Establish collaboration with ICES WG Bird on data collection, storage and analysis | Black backed gull, Little shearwater; Balearic shearwater; Black-legged kittiwake; Roseate tern; Iberian guillemot; Thick-billed murre | All | Germany and United kingdom |  |  |  | This action has been completed. OSPAR/HELCOM/ICES Joint Working Group on Seabirds (JWGBIRD) has been established. The group provides the expertise for collecting regional seabird data stored in an OSPAR biodiversity database hosted by ICES. JWGBIRD provides annual updates to ICG-POSH and ICG-COBAM. |
| 37 | Bring to the attention of relevant competent authorities the status of and threats, and the need for further research and data collection | Lesser black-backed gull; Ivory gull; Little shearwater; Balearic shearwater; Black-legged kittiwake; Roseate tern; Thick-billed murre | All | No Lead, supported by Norway ICG-POSH, ICG-COBAM. JWG Bird |  |  |  | Implementation of this action needs to be reconsidered, considered to be addressed through a regular cycle of assessments. |
| 38 | Further research on source populations, status and distribution and other causes for decline. This means to develop a research agenda on this topic/ species in national waters and ABNJ | Leatherback turtle, Loggerhead turtle | All | No Lead, supported by France ICG-POSH, ICG-COBAM, BDC |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. |
| 39 | Undertake further research the causes of decline in the Steller’s Eider, in particular through the Norwegian-Russian Environmental Commission | Steller’s eider | I | Norway |  |  |  | Initial survey/census of the total European winter population at approximately 10 years cycle was conducted in 2009. Discussions have been undertaken by Norway and Russia for a repeated survey. Annual ongoing monitoring of the Varanger winter population in combination to periods with frequent monitoring (monthly-winter 2016/17) contributes to a better understanding of their habitat usage and behavioural patterns |
| 40 | Seek advice on the latest knowledge of species and habitats supported by seamounts located within the OSPAR Maritime Area, then evaluate possible inclusion of these biological communities in the OSPAR List of Threatened and/or Declining Species and Habitats | Seamounts | I, IV, V | Norway and UK |  |  |  | A scoping study covering ca 100 surveyed seamounts has been completed. The study confirmed that seamounts are "hotspots" for biodiversity and VME's. Plankton, benthos and fish have been studied at 11, 24 and respective 16 seamounts, out of the estimated (modelled) 160 seamounts, in the OSPAR Maritime Area. The scoping study species list represents only 1.3% of all fish species on Earth, but 25% of all families and 45% of all orders. Very few seamounts in the OSPAR Regions I, IV and V have been subjected to extensive and systematic studies on plankton diversity. There has been no or little research on the ecological significance of seamounts or status of these vulnerable ecosystems. |
| 41 | Enhance knowledge exchange between researchers, and between researchers, management authorities and OSPAR | Roseate tern | II, III, IV and V | No lead ICG-POSH |  |  |  | This action has been completed. The implementation of Action 43 is anticipated to result in the establishment of an expert group on Roseate tern, which is considered to achieve the promotion of necessary knowledge exchange on this threatened seabird as per the goal of Action 41 through this WG future meetings |
| 42 | Compile and promote a list of useful future research areas that would inform the protection and conservation of Sabellaria spinulosa reefs to relevant scientific funding bodies and existing national monitoring programmes | Sabellaria spinulosa reefs | II and III | Netherlands |  |  |  | Development of action sheet not yet initiated |
| 43 | Promote implementation of the European Commission Species Action Plan for the species | Balearic shearwater, Roseate tern | II, III, IV and V | Spain |  |  |  | Implementation has been initiated. The lead party has identified experts from several Contracting Parties who would support implementation. A workshop to be held in Spain, February 2020, would bring together the experts to work on implementation of the action. A foreseen outcome is to establish an expert group of researchers and managers, along with the participation of JWGBIRD and BirdLife partners. |
| 44 | Promote the updating and implementation of the Arctic Council CAFF Action Plan (1996) | Thick-billed murre | I | No Lead, supported by Norway, ICG-POSH |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. |
| 45 | Develop and implement an OSPAR action plan for Lesser black-backed gull | Lesser black-backed gull | I | No Lead, Supported by Norway, ICG-POSH |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed. A supplementary explanation to the action needs to be developed with the aim to clarify the intention behind developing an ‘action plan’ and to what extent this document would go beyond actions in a Recommendation. |
| 46 | Request the international Council for the Exploration of the Seas (ICES) to continue to improve its assessment of the effectiveness of European and national management plans | European eel | I, II, III and IV | Secretariat |  |  |  | Implementation of this action needs to be reconsidered, an alternative approach to the development of actions sheets may be needed |